## Legacy Component Deliverables
LEGACY COMPONENT | COMPLETE | DELIVERY DATE | NOTES
Main process controller for all proccesses | 30% | 2017-08-11 | filename: ZHRI100A.SQR
New Hire/Rehire process for Employee | 30% | 2017-07-21 | filename: ZHRI101A.SQC
Termination process for Employee | 30% | 2017-07-28 | filename: ZHRI102A.SQC
Job Profile Changes process for Employee | 30% | 2017-08-04 | filename: ZHRI104A.SQC
Demographics Changes process for Employee | 30% | 2017-08-04 | filename: ZHRI105A.SQC
Date Changes process for Employee | 30% | 2017-08-04 | filename: ZHRI107A.SQC
Group Transfers process for Employee | 30% | 2017-08-11 | filename: ZHRI109A.SQC
Trigger History process | 30% | 2017-07-21 | filename: ZHRI110A.SQR
New Hire/Rehire process for Non-Person | 30% | 2017-07-21 | filename: ZHRI201A.SQC
Termination process for Non-Person | 30% | 2017-07-28 | filename: ZHRI202A.SQC
Demographic Change process for Non-Person | 30% | 2017-08-04 | filename: ZHRI205A.SQC
Start Date of POIs and Alternate EIDs | 30% | 2017-08-11 | filename: ZHRISTDT.SQR

## High Level Tasks
TASKS |  | DURATION WKS | COMPLETE
Setup Workspace |  | 1 | 100%
Setup Development Platform |  | 1 | 90%
System Analysis and Design:
| Understand legacy system | 1 | 100%
| Understand design of proposed system | 1 | 95%
| Document design of proposed system | 1 | 90%
System Implementation:
| Trigger Monitor | 2 | 5%
| Data Importer | 2 | 0%
| Data Translator | 3 | 0%
| Data Exporter | 3 | 0%
Testing:
| Test Plan | 1 | 0%
| Test Suite | 1 | 0%

## Low Level Tasks
TASKS |  |  | COMPLETE
Setup Workspace
| Outlook; IT Time Tracking; Journalx; Tech Partners Timesheet; JIRA; Confulence; Request-it; Office Supplies |  | 100%
| Setup remote access |  | 100%
Setup Development Platform:
| STS IDE; Oracle SQL Developer; Maven; JPA; Git; HipChat; Notepad++ |  | 100%
| DB2 DBA Tool for AS/400 RDBMS |  | 0%
| Setup code repository for implemention phase in BitBucket |  | 50%
| Setup Jenkins for continous build and testing |  | 5%
| Setup Artifactory for artifact storage |  | 0%
System Analysis and Design Tasks
| Meetings with Architect to get understanding of the legacy system |  | 100%
| Meetings with Architect to get understanding of the proposed system |  | 100%
| Review legacy system design documentation |  | 100%
| Review proposed system design documentation |  | 100%
| Discuss changes to proposed system design with Architect |  | 100%
| Meetings with DBA to get understanding of database components |  | 80%
| Analyze PeopleSoft procedure code in .sqr and .sqc files |  | 100%
| Convert PeopleSoft procedure code into pseudocode |  | 20%
| Determine which data structures and design patterns to use for implementation |  | 90%
Document System Analysis and Design
|  | Update high-level architecture documents | 100%
|  | Create low-level architecture documents | 100%
|  | Create table describes for each PS table used | 100%
|  | Create dataflow diagrams for proposed system | 100%
|  | Create detailed design for Trigger Monitor component | 90%
|  | Create detailed design for Data Importer component | 90%
|  | Create detailed design for Data Translator component | 90%
|  | Create detailed design for Data Exporter component | 90%
|  | Create deployment strategy document | 0%
| Meetings with QA to get an understanding of user test requirements |  | 0%
| Create user test suite |  | 0%
System Implementation Tasks
| Create proof-of-concept Java application |  | 100%
| Create PS database server connection through Java |  | 99%
| Create AS/400 database server connection through Java |  | 0%
| Create JPA entities for PS tables |  | 5%
| Create JPA entities for AS/400 tables |  | 0%
| Create CRUD methods for all tables |  | 5%
| Convert PeopleSoft pseudocode into Java code where appropriate |  | 0%
| Create unit test suite |  | 2%
| Create Trigger Monitor component |  | 5%
| Create Data Importer component |  | 0%
| Create Data Translator component |  | 0%
| Create Data Exporter component |  | 0%